{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","PERT"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":33,"n_cols":8,"rows_kept":33,"cut":false,"hidden":false,"merged":[]}
["Activity","Activity Description","Stage","Method","Deliverables/Decsions Made","Predecessors","Start Time","Duration (weeks)"]
["α","Determine necessary Training  Materials","Research Step",null,null,"Start",0,2]
["β","RISE app approval by app store","Research Step",null,null,"Start",0,2]
["χ","RISE app bugs worked out by team","Research Step",null,null,"Start",0,4]
["δ","updated RISE app excepted by app store","Research Step",null,null,"χ",4,1]
["ε","RISE app is ready for patient use","Research Step",null,"Usable RISE app","β,δ",5,0]
["η","Develop missing Training Materials",null,null,"Training Materials","α,χ",4,3]
["A","Cara sends emails to all Orgs","Recruitment","Email from IDPH",null,"Start",0,0.5]
["B","Interested Orgs have initial call with Cara","Recruitment","Call with Cara",null,"A",0.5,1.5]
["C","CHESS emails orgs to confirm interest and potential site selection","Interest","Email from CHESS","Inital Site Confirmations","B",2,0.5]
["D","CHESS has call with organization to understand how the Org opperates - Call 0","Confirmation and continued interest","Call with CHESS","Organization Profile (w/ specifics such as clinic size and # / types of staff, etc.)","C",2.5,1.5]
["E","Follow up email w/ org to finalize site selections and coordinators","Confirmation and continued interest",null,"Finalize Participating Sites, Determine","D",4,0.5]
["F","Get Integreview Approved","Research Step",null,null,"Start",0,3]
["G","Organization is confirmed and is ready to be randomized","Confirmation and continued interest",null,null,"D,F",4,0.5]
["H","Take Organizational Survery","Inital Survey","RedCap","financial readiness","G,E",4.5,2]
["I","Take Staff Surveys","Inital Survey","RedCap","OCM","G,E",4.5,2]
["J","Confirm Scoring proccedures for randomization","Research Step",null,null,"Start",0,2.5]
["K","Create Pairs of Organizations","Research Step",null,null,"J,G",4.5,0.5]
["L","Randomize","Research Step",null,"Intervention and Control Groups","K",5,1]
["M","Call 1","Intervention - Implementation","Call with Coach nad ED",null,"L",6,2]
["N","Call 2","Intervention - Implementation","Call with Coach and Site Coordinator",null,"H,I,M,η",8,2]
["O","Identification of Implementation Team","Intervention - Implementation","pre-work","implementation team selected","N",10,2]
["P","Scheduling of Site visits intervention","Intervention - Implementation",null,null,"L",6,0.5]
["Q","1st in person visit","Intervention - Implementation",null,null,"O,P,ε",12,0.5]
["R","Call following up 1st visit","Intervention - Implementation",null,null,"L",6,1.5]
["S","2nd in person visit","Intervention - Implementation",null,null,"P,R",7.5,0.5]
["T","Monthly individual Coaching calls","Intervention - Implementation",null,null,"S",8,4]
["U","Quarterly Group Calls","Intervention - Implementation",null,null,"S",8,2]
["V","Sustainability tool and assessment","Intervention - Implementation",null,null,"S",8,4]
["W","Quarterly calls with mangement","Intervention - Implementation",null,null,"V",12,1]
["X","Call - control","Control -Implementation","With Chess Trainer and Site Leader",null,"L,η",7,2]
["Y","Scheduling of Site visits intervention","Control -Implementation",null,null,"L",6,0.5]
["Z","On site Training","Control -Implementation",null,null,"X,Y,ε",9,0.5]

{"sheet":"Sheet2","index":1,"n_rows":28,"n_cols":32,"rows_kept":28,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Control"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null," Intervention"]

{"sheet":"PERT","index":2,"n_rows":43,"n_cols":23,"rows_kept":43,"cut":false,"hidden":false,"merged":[[26,2,26,3]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null," Intervention"]
[]
[]
[]
[]
[]
["Legend"]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Control"]
[null,null,"Potential bottleneck"]
[]
[]
[null,null,"Node is along critial path"]
[]
[]
[null,null,null,null,"Tasks along the Critical Path"]
[null,null,null,null,"Activity","Start Time","Duration","Description"]
[null,null,null,null,"A",0,0.5,"Cara sends emails to all Orgs"]
[null,null,null,null,"B",0.5,1.5,"Interested Orgs have initial call with IDPH"]
[null,null,null,null,"C",2,0.5,"CHESS emails orgs to confirm interest and potential site selection"]
[null,null,null,null,"D",2.5,1.5,"CHESS has call with organization to understand how the Org opperates - Call 0"]
[null,null,null,null,"G",4,0.5,"Organization signs contract"]
[null,null,null,null,"J",4.5,2.5,"Confirm Scoring proccedures for randomization"]
[null,null,null,null,"K",7,0.5,"Create Pairs of Organizations"]
[null,null,null,null,"L",7.5,1,"Randomize"]
[null,null,null,null,"M",8.5,2,"Call 1"]
[null,null,null,null,"N",10.5,2,"Call 2"]
[null,null,null,null,"O",12.5,2,"Identification of Implementation Team"]
[null,null,null,null,"P",14.5,0.5,"1st in person visit"]